## Dashboard
🎓 CS50x — The Finish-Line Dashboard
Current | Week 2 — Arrays ✅ |  | Finished | 20 Aug 2026 | School | 23 Sep 2026 (1 Mehr)
MISSION 01 → Finish the hard C core before school
Week 3 | Algorithms | 24 Aug – 1 Sep | 🔴 HARD
Week 4 | Memory | 2 – 9 Sep | 🔴 HARD
Week 5 | Data Structures | 10 – 17 Sep | 🔴 HARD
Week 6 | Python | 18 – 22 Sep | 🟡 LIGHTER
MISSION 02 → Finish CS50x before winter
Week 7 | SQL | 24 Sep – 1 Oct
Week 8 | HTML / CSS / JavaScript | 2 – 9 Oct
Week 9 | Flask | 10 – 18 Oct
Week 10 | Final Project | 19 Oct – 15 Nov
🏁 TARGET: CS50x completed by 15 Nov 2026 ¦ Esfand deadline = safety margin, not the goal

## Roadmap
Week | Topic | Start | Target Finish | Phase | Priority | Status | Main Output
Week 0 | Scratch | Jul 2026 | Jul 2026 | Completed | — | ✅ Done | Scratch project
Week 1 | C | Aug 2026 | Aug 2026 | Completed | — | ✅ Done | PSet 1
Week 2 | Arrays | — | 20 Aug 2026 | Completed | — | ✅ Done | Caesar + Readability + Scrabble
Week 3 | Algorithms | 24 Aug 2026 | 1 Sep 2026 | Hard Core | P1 | ⬜ | PSet 3
Week 4 | Memory | 2 Sep 2026 | 9 Sep 2026 | Hard Core | P1 | ⬜ | PSet 4
Week 5 | Data Structures | 10 Sep 2026 | 17 Sep 2026 | Hard Core | P1 | ⬜ | PSet 5
Week 6 | Python | 18 Sep 2026 | 22 Sep 2026 | Pre-school Finish | P1 | ⬜ | PSet 6
Week 7 | SQL | 24 Sep 2026 | 1 Oct 2026 | School Mode | P1 | ⬜ | PSet 7
Week 8 | HTML / CSS / JavaScript | 2 Oct 2026 | 9 Oct 2026 | School Mode | P1 | ⬜ | PSet 8
Week 9 | Flask | 10 Oct 2026 | 18 Oct 2026 | School Mode | P1 | ⬜ | PSet 9
Week 10 | Final Project | 19 Oct 2026 | 15 Nov 2026 | Capstone | P1 | ⬜ | Final project + docs + video

## Weekly Tracker
Week | Lecture | Notes PDF | PSet / Project | Submit | Check ≥70% | GitHub Commit | Reflection
Week 0 | ✅ | 📄 | ✅ | ✅ | ≥70% | Done
Week 1 | ✅ | 📄 | ✅ | ✅ | ≥70% | Done
Week 2 | ✅ | 📄 | ✅ | ✅ | ≥70% | Done
Week 3 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 4 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 5 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 6 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 7 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 8 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜
Week 9 | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜

## Rules
CS50x Personal Rules
🟢 Green | Already know it | 0–5 lines in handbook
🟡 Yellow | Some new detail | Short focused note
🔴 Red | New / difficult concept | Deep notes + examples + mental model
🎯 Main rule | PSet first, notes second | The problem set is the real test of understanding
🧠 Integrity | No solution-copying | Use help to understand, not to outsource the work
📦 GitHub | One polished weekly commit | Notes PDF + weekly README + solutions